Project Overview

| Item | Details |
| --- | --- |
| Project | Bunga Raya Wellhead Platform T&I |
| Client | PetroEnergy Malaysia |
| Contract Value | USD 68 million |
| Offshore Location | Sarawak Basin |
| Planned Completion | 30 September 2026 |
| Current Reporting Period | August 2026 |

Overall Progress

Engineering

- Planned: 100%

- Actual: 98%

- Remaining work:

  - Final vendor drawing approvals

  - Closure of two engineering comments

Procurement

- Planned: 95%

- Actual: 91%

- Outstanding:

  - Delivery of 12 control valves

  - Customs clearance for ROV spare parts

Fabrication

- Planned: 90%

- Actual: 88%

- Remaining activities:

  - Mechanical completion walkdown

  - Punch list closure (18 items)

Marine Operations

- Heavy lift vessel mobilization delayed.

- Original mobilization date: 15 August 2026.

- Revised mobilization date: 22 August 2026.

HSE Performance

Positive Highlights

- Zero Lost Time Injuries (LTI).

- 245,000 safe man-hours achieved.

- No environmental incidents.

- 100% toolbox talk compliance.

Concerns

- Two near-miss incidents reported:

  - Improper lifting sling storage.

  - Personnel entering restricted area without authorization.

Corrective actions have been implemented.

Schedule Status

Key Issue

Heavy lift vessel arrival was delayed due to adverse weather conditions and previous commitments on another campaign.

Schedule Impact

- Original offshore campaign start:

  - 18 August 2026

- Revised offshore campaign start:

  - 25 August 2026

- Estimated project completion delay:

  - 5 calendar days

Commercial Status

Approved Budget

USD 68 million

Current Forecast

USD 68.9 million

Variance

USD 0.9 million over budget.

Main Contributors

- Vessel standby costs:

  - USD 250,000

- Expedited logistics:

  - USD 180,000

- Additional offshore preparation activities:

  - USD 470,000

Key Risks

Risk 1

Heavy lift vessel availability.

Potential Impact:

- Further schedule delays.

Mitigation:

- Alternative vessel identified.

- Daily coordination with vessel owner.

Risk 2

Adverse monsoon weather.

Potential Impact:

- Reduced offshore workability.

Mitigation:

- Optimized installation sequence.

- Additional weather forecasting support.

Risk 3

Late delivery of critical control valves.

Potential Impact:

- Commissioning delay.

Mitigation:

- Air freight arrangement under evaluation.