Dear Team,

We would like to inform that the shipment scheduled for 15 Aug 2026 may face a delay of 7–10 days.

During final inspection, our production team found that the connector type specified in the latest drawing differs from the original PO. This requires additional tooling adjustment.

We apologize for inconvenience caused and request clarification on which version should be followed.

Best regards,
Li Wei

From: Ahmad (Procurement – HQ)
To: Li Wei
CC: Project Team
Date: Tue, 4 Aug 2026, 10:02 AM

Hi Li Wei,

This is concerning as the PO was already confirmed in September.

The Vietnam plant is planning production based on the agreed delivery date.

Please advise why this was only discovered now and whether the original connector can still be used.

Regards,
Ahmad

From: Nguyen Thi Lan (Vietnam Manufacturing Partner)
To: Project Team
CC: Operations Manager
Date: Tue, 4 Aug 2026, 11:15 AM

Dear All,

We are very worried about the delay.

Our assembly line is scheduled to start on 18 Aug 2026, and any delay will impact manpower planning and customer commitments.

Please confirm urgently whether the shipment will arrive as planned.

Thank you,
Lan

From: Li Wei
To: Ahmad
CC: Project Team
Date: Tue, 4 Aug 2026, 1:40 PM

Dear Ahmad,

Thank you for your message.

Based on our records, the original PO drawing (Rev A) differs from the updated drawing (Rev B) shared on 10 Jul 2026.

Our team followed the latest version received.

We understand the urgency and are checking if partial shipment is possible.

However, this may increase cost.

We seek your understanding.

Best regards,
Li Wei

From: Ahmad
To: Project Team
CC: Finance
Date: Tue, 4 Aug 2026, 3:05 PM

Team,

This issue is now affecting cost, schedule, and customer confidence.

We need to understand:

- Which drawing is contractually valid

- Why change management failed

- Cost impact if partial shipment is required

Please advise ASAP.

Thanks,
Ahmad

From: Sarah (Project Manager)
To: All
CC: Senior Management
Date: Tue, 4 Aug 2026, 4:20 PM

Dear Everyone,

Let's align and avoid further confusion.

Action items:

• China supplier to confirm feasibility of partial shipment by tomorrow
• Vietnam team to assess impact of 7–10 day delay
• Procurement to verify contract drawing version

We should focus on solution and mitigation, not fault.

Regards,
Sarah

From: Nguyen Thi Lan
To: Sarah
CC: Senior Management
Date: Wed, 5 Aug 2026, 9:10 AM

Dear Sarah,

Thank you for coordination.

However, I must highlight that even a one-week delay will require overtime work and may affect quality and safety.

We need confirmation today to proceed with manpower planning.

Best regards,
Lan

From: Li Wei
To: Project Team
CC: Procurement
Date: Wed, 5 Aug 2026, 10:30 AM

Dear Team,

After internal discussion, we can propose:

• Partial shipment of compliant units by 18 Aug 2026
• Remaining units by 25 Aug 2026

Additional cost estimate will be shared shortly.

We hope this demonstrates our commitment to cooperation.

Best regards,
Li Wei