## Project Activities
Activity ID | Activity Name | Project Phase | Start Date | Planned Finish | Actual Finish | Budget (USD) | Actual Cost (USD) | % Complete | Status | Resource
A001 | Engineering Design | Engineering | 1-Jan-26 | 15-Jan-26 | 14-Jan-26 | 25000 | 24000 | 100 | Completed | John
A002 | Material Procurement | Procurement | 5-Jan-26 | 30-Jan-26 | 5-Feb-26 | 45000 | 52000 | 100 | Delayed | Sarah
A003 | Fabrication | Construction | 1-Feb-26 | 28-Feb-26 | 10-Mar-26 | 120000 | 135000 | 100 | Delayed | Michael
A004 | Loadout Preparation | Logistics | 15-Feb-26 | 20-Feb-26 | 21-Feb-26 | 15000 | 18000 | 100 | Delayed | David
A005 | Offshore Transportation | Marine | 1-Mar-26 | 5-Mar-26 |  | 85000 | 72000 | 75 | In Progress | Jason
A006 | Platform Installation | Offshore | 6-Mar-26 | 15-Mar-26 |  | 200000 | 150000 | 60 | In Progress | Kevin
A007 | Hook-Up Activities | Offshore | 16-Mar-26 | 30-Mar-26 |  | 95000 | 30000 | 25 | In Progress | Amy
A008 | Mechanical Completion | Commissioning | 1-Apr-26 | 15-Apr-26 |  | 50000 | 0 | 0 | Not Started | Richard
A009 | Pre-Commissioning | Commissioning | 16-Apr-26 | 25-Apr-26 |  | 40000 | 0 | 0 | Not Started | Richard
A010 | Final Handover | Closeout | 26-Apr-26 | 30-Apr-26 |  | 15000 | 0 | 0 | Not Started | PM

## Resource Utilization
Resource | Department | Planned Hours | Actual Hours | Billable Rate | Overtime Hours
John | Engineering | 120 | 105 | 100 | 0
Sarah | Procurement | 160 | 185 | 95 | 25
Michael | Fabrication | 220 | 260 | 90 | 40
David | Logistics | 80 | 95 | 85 | 15
Jason | Marine | 140 | 130 | 120 | 5
Kevin | Offshore | 250 | 290 | 130 | 45
Amy | Offshore | 180 | 140 | 110 | 0
Richard | Commissioning | 150 | 90 | 100 | 0

## Risk Register
Risk ID | Risk Description | Probability | Impact | Risk Score | Status
R001 | Fabrication delay | High | High | 25 | Open
R002 | Vessel availability issue | Medium | High | 15 | Open
R003 | Bad weather offshore | Medium | High | 15 | Open
R004 | Material shortage | High | Medium | 20 | Mitigated
R005 | Crane breakdown | Low | High | 10 | Open
R006 | Manpower shortage | Medium | Medium | 9 | Open
R007 | Safety incident | Low | Very High | 15 | Open
R008 | Supplier quality issue | Medium | Medium | 9 | Closed

## Monthly Cost Trend
Month | Planned Cost | Actual Cost
Jan-26 | 70000 | 76000
Feb-26 | 120000 | 153000
Mar-26 | 180000 | 205000
Apr-26 | 140000 | 130000
May-26 | 90000 | 0