COMMERCIAL PROPOSAL

PROVISION OF TRANSPORTATION AND OFFSHORE INSTALLATION WORKS FOR SLDP-A WELLHEAD PLATFORM

Submitted By:
HHI Offshore Services Sdn Bhd

Proposal No:
HHI-COMM-SLDPA-2025-001

Date:
31 July 2025

Currency:
USD

Validity:
180 Days

1. COMMERCIAL EXECUTIVE SUMMARY

HHI Offshore Services Sdn Bhd is pleased to submit our commercial proposal for the Transportation and Offshore Installation Works for the SLDP-A Wellhead Platform Project.

The proposal is based on the technical scope defined in ITB DH24010/DECSB/VC-PL/80.30/ITB and subsequent clarification responses received up to 24 July 2025.

The commercial proposal is based on a single mobilization campaign utilizing DB HHI TITAN and associated marine spread.

2. COMMERCIAL PRICE SCHEDULE

2.1 Base Scope Pricing

| Item | Description | Amount (USD) |
| --- | --- | --- |
| A | Engineering & Project Management | 185,000 |
| B | Mobilization of Derrick Barge | 420,000 |
| C | Demobilization of Derrick Barge | 350,000 |
| D | Derrick Barge Offshore Campaign (21 Days) | 1,850,000 |
| E | Anchor Handling Tug Support | 425,000 |
| F | Utility Vessel Support | 185,000 |
| G | Offshore Installation Activities | 790,000 |
| H | Documentation & Closeout | 55,000 |

Total Base Scope Price

USD 4,260,000

3. OPTIONAL PRICING

The following items are not included in the base scope and shall only be performed upon COMPANY instruction.

Option 1 – Additional Offshore Campaign

| Item | Rate |
| --- | --- |
| Derrick Barge Daily Rate | USD 88,000/day |
| AHTS Daily Rate | USD 18,500/day |
| Utility Vessel Daily Rate | USD 7,500/day |

Option 2 – Additional Engineering Support

| Item | Amount |
| --- | --- |
| Additional Engineering Manhour | USD 120/hour |

Option 3 – Additional Survey Support

| Item | Amount |
| --- | --- |
| Survey Team Mobilization | USD 45,000 |
| Survey Daily Rate | USD 3,500/day |

4. PRICING ASSUMPTIONS

The pricing is based on the following assumptions:

- Offshore campaign duration shall not exceed twenty-one (21) days.

- Fabrication works shall be completed prior to vessel mobilization.

- COMPANY shall provide approved construction drawings before mobilization.

- COMPANY shall provide Marine Warranty Surveyor approval requirements.

- Offshore weather downtime allowance is limited to three (3) days.

- Port charges at fabrication yard are by COMPANY account.

- Customs duties and import permits are by COMPANY account.

- No standby charges are included beyond the agreed campaign duration.

5. COMMERCIAL EXCLUSIONS

The following items are excluded from this proposal:

- Certifying Authority services.

- Risk Based Inspection (RBI) activities.

- Independent third-party verification.

- Geotechnical survey services.

- Metocean studies.

- Environmental Impact Assessment.

- Helicopter services.

- Accommodation Work Barge (AWB).

- Additional support vessel beyond proposed marine spread.

- Subsea inspection services.

- Pipeline installation works.

- Hook-up and commissioning works.

6. COMMERCIAL QUALIFICATIONS

HHI's proposal is based on the following qualifications:

- All platform weights provided in the ITB are final.

- Any increase exceeding 5% in structure weight shall constitute a variation order.

- Offshore execution shall be performed within the agreed weather window.

- Changes in offshore installation sequence may result in commercial adjustments.

- Delays caused by fabrication readiness shall be chargeable as standby.

- Delays due to adverse weather beyond agreed allowance shall be chargeable.

7. POTENTIAL VARIATION RATES

Vessel Standby

| Item | Rate |
| --- | --- |
| DB HHI TITAN | USD 65,000/day |
| AHTS Pioneer | USD 14,500/day |
| AHTS Venture | USD 14,500/day |
| Utility Vessel | USD 6,500/day |

Additional Personnel

| Position | Rate |
| --- | --- |
| Offshore Installation Engineer | USD 950/day |
| Construction Supervisor | USD 750/day |
| HSE Officer | USD 650/day |

8. TAXATION

The proposal excludes:

- Withholding Tax (WHT)

- Sales and Service Tax (SST)

- Import Duties

- Customs Charges

- Other Government Levies

All taxes shall be borne by COMPANY unless otherwise stated in the Contract.

9. PAYMENT TERMS

| Milestone | Percentage |
| --- | --- |
| Contract Award | 15% |
| Mobilization | 25% |
| Completion of Transportation | 20% |
| Completion of Jacket Installation | 20% |
| Completion of Deck Installation | 15% |
| Final Documentation Submission | 5% |

Payment Due:

Thirty (30) days from receipt of invoice.

10. BIDDER EXCEPTIONS

| No | Exception | Commercial Impact |
| --- | --- | --- |
| 1 | Certifying Authority excluded | Additional cost if required |
| 2 | RBI excluded | Additional cost if required |
| 3 | Voyage Insurance excluded | Additional cost if required |
| 4 | AWB not included | Additional vessel cost if required |

11. CURRENCY AND EXCHANGE RATE

Currency:
USD

Reference Exchange Rate:

USD 1.00 = MYR 4.287

Any exchange fluctuation exceeding ±5% from bid closing date shall be subject to commercial adjustment.

12. COMMERCIAL RISK ITEMS

The following items may impact the final project cost:

- Requirement for Accommodation Work Barge due to increased offshore manpower.

- Additional lifting operations if platform weight exceeds current assumptions.

- Additional campaign duration due to weather delays.

- Additional support vessels required by COMPANY.

- Additional certification requirements imposed after award.

- Additional survey requirements imposed by Marine Warranty Surveyor.

13. COMMERCIAL VALIDITY

This proposal shall remain valid for 180 calendar days from the bid closing date.

14. COMMERCIAL DECLARATION

HHI Offshore Services Sdn Bhd confirms that the commercial proposal has been prepared based on the information made available during the tender process and remains subject to final contract negotiations.

Authorized Signatory

Commercial Director

HHI Offshore Services Sdn Bhd

15. DETAILED COST BREAKDOWN

15.1 Marine Spread Pricing

| Item | Unit | Qty | Rate (USD) | Amount (USD) |
| --- | --- | --- | --- | --- |
| DB HHI TITAN Mobilization | LS | 1 | 420,000 | 420,000 |
| DB HHI TITAN Demobilization | LS | 1 | 350,000 | 350,000 |
| DB HHI TITAN Offshore Campaign | Day | 21 | 88,000 | 1,848,000 |
| AHTS Pioneer | Day | 21 | 18,500 | 388,500 |
| AHTS Venture | Day | 21 | 18,500 | 388,500 |
| Utility Vessel | Day | 21 | 7,500 | 157,500 |

Subtotal:
USD 3,552,500

15.2 Engineering Pricing

| Item | Amount (USD) |
| --- | --- |
| Project Management | 75,000 |
| Transportation Analysis | 45,000 |
| Lift Engineering | 35,000 |
| Installation Procedure | 25,000 |
| Closeout Documentation | 5,000 |

Subtotal:
USD 185,000

16. MARINE SPREAD COMMERCIAL MATRIX

| Vessel | Included | Daily Rate |
| --- | --- | --- |
| Derrick Barge | Yes | Included |
| AHTS #1 | Yes | Included |
| AHTS #2 | Yes | Included |
| Utility Vessel | Yes | Included |
| Standby Vessel | No | USD 9,500/day |
| Accommodation Work Barge (AWB) | No | USD 28,000/day |
| Crew Boat | No | USD 4,500/day |
| Survey Vessel | Optional | USD 6,500/day |

Commercial Note:

The proposed marine spread does not include AWB or Standby Vessel unless specifically instructed by COMPANY.

17. ACCOMMODATION & POB BASIS

Proposed Accommodation

| Item | Capacity |
| --- | --- |
| DB HHI TITAN | 220 POB |
| Utility Vessel | 80 POB |

Total Available POB:
300

Pricing Assumption

Commercial pricing is based on:

Maximum Offshore Manpower:
180 personnel

No Accommodation Work Barge required.

Commercial Adjustment Basis

Should offshore manpower exceed 180 personnel, additional AWB may be required.

Indicative AWB Cost:

| Item | Amount |
| --- | --- |
| Mobilization | USD 180,000 |
| Demobilization | USD 150,000 |
| Daily Charter | USD 28,000/day |

18. CRANE CAPACITY COMMERCIAL IMPACT

Proposed Lift Capability

Main Crane Capacity:
2,500 MT

Maximum Deck Lift:
1,200 MT

Maximum Jacket Lift:
750 MT

Commercial Basis

Proposal assumes:

Single Lift Installation Philosophy.

Potential Cost Impact

Should COMPANY revise platform weight requiring multiple lift execution:

| Item | Amount |
| --- | --- |
| Additional Engineering | USD 95,000 |
| Additional Offshore Duration | USD 440,000 |
| Additional Marine Spread | USD 220,000 |

Estimated Cost Impact:

USD 755,000

19. COMMERCIAL DEVIATION REGISTER

| No | Commercial Deviation |
| --- | --- |
| 1 | Certifying Authority excluded |
| 2 | RBI excluded |
| 3 | Voyage Insurance excluded |
| 4 | AWB excluded |
| 5 | Helicopter services excluded |
| 6 | Geotechnical survey excluded |
| 7 | Additional support vessel excluded |
| 8 | SST excluded |
| 9 | WHT excluded |
| 10 | Import duties excluded |

Potential Commercial Impact

The above items may require commercial adjustment during evaluation if COMPANY decides they form part of the required scope.

20. TAX & CURRENCY SCHEDULE

Currency

Proposal Currency:
USD

Reference Exchange Rate:

1 USD = MYR 4.287

Tax Treatment

| Tax Item | Included |
| --- | --- |
| SST | No |
| WHT | No |
| Import Duty | No |
| ITS | No |
| Customs Charges | No |

Commercial Evaluation Basis

All taxes shall be applied by COMPANY during commercial evaluation to establish normalized comparison.

21. NORMALIZATION COST SCHEDULE

The following budgetary figures are provided solely for commercial normalization purposes.

Certifying Authority

Estimated Cost:
USD 35,000

Risk Based Inspection

Estimated Cost:
USD 45,000

Voyage Insurance

Estimated Cost:
USD 120,000

AWB Requirement

Estimated Cost:

| Item | Amount |
| --- | --- |
| Mobilization | USD 180,000 |
| Demobilization | USD 150,000 |
| Charter (21 Days) | USD 588,000 |

Total:
USD 918,000

Additional Standby Vessel

Estimated Cost:

USD 9,500/day

22. BID CLARIFICATION RESPONSES

Clarification 1

Question:

Please confirm whether AWB is included.

Response:

AWB is excluded.

Pricing assumes available accommodation capacity is sufficient.

Clarification 2

Question:

Please confirm whether Voyage Insurance is included.

Response:

Voyage Insurance is excluded from our base scope.

Clarification 3

Question:

Please confirm tax treatment.

Response:

Proposal excludes SST, WHT, Import Duty and other statutory charges.

Clarification 4

Question:

Please provide exchange rate basis.

Response:

USD/MYR 4.287 as at bid closing date.

Clarification 5

Question:

Please confirm standby rates.

Response:

Standby rates are stated in Section 7 of this proposal.

COMMERCIAL RISK SUMMARY

| Risk | Potential Impact |
| --- | --- |
| AWB Requirement | Medium |
| Additional Offshore Duration | Medium |
| Weather Delay | Medium |
| Weight Growth | High |
| Additional Certification Requirement | Low |
| Exchange Rate Movement | Medium |
| Tax Interpretation | Medium |

These risks should be considered during Commercial Bid Evaluation and bid normalization.

BID IMPROVEMENT TABLE

| Issue | Why It Hurts Bid Competitiveness | Recommended Improvement | Expected Benefit |
| --- | --- | --- | --- |
| Too many visible exclusions in base scope | The proposal may appear less complete, and COMPANY may normalize additional costs during evaluation, reducing price competitiveness. | Consider including selected high-visibility items such as Voyage Insurance, Certifying Authority, or limited certification support in the base scope, or offer them as a bundled alternate option. | Improves perceived completeness and reduces negative normalization impact. |
| AWB excluded while total indicative cost is high | A potential AWB add-back of USD 918,000 is significant and may lead evaluators to assume the final cost could be materially higher. | Strengthen the manpower basis by providing a clear offshore manning plan showing why 180 personnel is sufficient, or offer AWB as a priced alternate option with a defined cap. | Reduces evaluator uncertainty and improves confidence that the base offer is executable without major add-backs. |
| Weight growth above 5% triggers variation | The variation trigger may be seen as a major commercial risk, especially since the estimated cost impact for multiple lifts is USD 755,000. | Provide stronger engineering justification for the single-lift basis, clarify available lift margin, and if possible offer a stepped adjustment mechanism instead of a broad variation trigger. | Makes the proposal look more robust and lowers concern over post-award cost escalation. |
| Commercial qualifications and standby wording are rigid | Phrases such as chargeable standby and variation order may make the bid look heavily qualified and transfer too much risk to COMPANY. | Reword selected clauses to sound more collaborative, for example subject to mutual review and agreement based on actual impact, while keeping commercial protection intact. | Improves commercial tone and reduces the perception of a defensive bid. |
| Executive summary is too brief and does not sell value strongly | Evaluators may see the proposal as price-and-risk focused rather than solution-and-value focused. | Expand the executive summary to highlight key differentiators such as single mobilization efficiency, integrated marine spread, offshore installation experience, and execution confidence. | Strengthens the overall bid narrative and helps position the offer beyond headline price. |
| Payment terms may be seen as slightly contractor-favorable | A 15% payment at award and 25% at mobilization may be acceptable, but in a competitive tender, client-friendlier terms can be a differentiator. | Consider a more balanced milestone profile or tie more value to visible execution milestones without materially weakening cash flow. | May improve commercial attractiveness and reduce negotiation resistance. |
| Taxes and exchange adjustment create normalization exposure | Excluded taxes and exchange fluctuation adjustments can make the evaluated price look less firm when compared with offers carrying fewer conditions. | Where possible, clarify fixed validity for optional rates, explain the tax basis more clearly, and consider whether exchange adjustment thresholds can be softened or capped. | Improves price certainty and supports a stronger normalized commercial position. |
| Proposal does not provide a lower-deviation commercial alternative | If COMPANY prefers a more complete commercial package, the current proposal gives limited flexibility. | Add an alternate offer with fewer exclusions, for example including Voyage Insurance, Certifying Authority, and a clearer AWB basis. | Gives evaluators a more client-aligned option and can improve ranking even if the base offer remains unchanged. |