Project Overview

Project Name: Orion Capacity Expansion Program

Customer: Global Semiconductor Manufacturing Customer

Location: Penang, Malaysia

Project Sponsor: Director of Customer Operations

Project Manager: Alex Tan

Project Objective:

Install and qualify one additional plasma etch production line to support increased wafer demand. The project aims to increase customer production capacity by 20% while maintaining existing quality standards and safety requirements.

Project Duration:

January 2026 – September 2026

Overall Budget:

USD 5.2 Million

Current Project Status:

Amber

Overall Completion:

68%

Key Achievements This Quarter

Installation Progress

- Mechanical installation completed for all major tool modules.

- Utility hookups completed ahead of schedule.

- Factory acceptance documentation approved by customer.

- Initial software integration testing successfully completed.

Team Performance

- Achieved zero safety incidents.

- Cross-functional teams maintained over 95% milestone adherence.

- Customer feedback indicated strong communication and responsiveness.

Cost Performance

- Actual spending remains within approved budget.

- Savings achieved through consolidated vendor deliveries.

- Travel costs reduced through increased remote support activities.

Current Challenges

Supplier Delays

One critical RF generator component experienced a two-week shipment delay due to supplier production constraints.

Impact:

- Qualification activities may be delayed.

- Resource rescheduling is required.

Mitigation Actions:

- Expedite logistics arrangements.

- Coordinate temporary resource reassignment.

- Increase testing shifts once components arrive.

Customer Scope Change

The customer requested additional process validation activities not included in the original project scope.

Impact:

- Additional engineering effort required.

- Potential increase in project duration.

Mitigation Actions:

- Initiate change control process.

- Evaluate resource requirements.

- Present revised estimates for approval.

Resource Constraints

Two field service engineers will be unavailable during the next project phase because of overlapping commitments.

Impact:

- Reduced installation support capacity.

Mitigation Actions:

- Engage regional support teams.

- Prioritize critical activities.

- Adjust shift schedules.

Financial Summary

Approved Budget: USD 5.2 Million

Actual Spend: USD 3.4 Million

Forecast at Completion: USD 5.35 Million

Variance:

- Approximately 3% above baseline forecast due to scope changes.

Cost Drivers:

- Additional validation requirements.

- Supplier recovery efforts.

- Overtime during qualification activities.

Schedule Summary

Major Milestones:

| Milestone | Planned Date | Status |
| --- | --- | --- |
| Project Kick-off | Jan 2026 | Completed |
| Tool Delivery | Mar 2026 | Completed |
| Mechanical Installation | May 2026 | Completed |
| Utility Integration | Jun 2026 | Completed |
| Software Testing | Jul 2026 | Completed |
| Process Qualification | Aug 2026 | In Progress |
| Customer Acceptance | Sep 2026 | Upcoming |

Overall Schedule Health:

- Approximately one week behind baseline.

- Recovery plan currently under execution.

Risks Requiring Leadership Attention

Risk 1: Supplier Recovery

Probability: High

Impact: High

Decision Required:
Approve expedited logistics budget of USD 80,000.

Risk 2: Scope Expansion

Probability: Medium

Impact: High

Decision Required:
Approve additional engineering support resources.

Risk 3: Resource Availability

Probability: Medium

Impact: Medium

Decision Required:
Authorize temporary support from regional teams.

Opportunities

- Standardize qualification templates across future installations.

- Increase use of remote diagnostics to reduce travel expenses.

- Develop reusable playbooks for customer onboarding.

- Improve supplier visibility through earlier escalation mechanisms.